STEWARDSHIP COMMITTEE ANNUAL PLAN

We encourage Stewardship Committees to make a detailed yearly plan that includes the organization and preparation for the 2-3 weekend effort as well as monthly awareness activities.  There are many ways to do this and someone in your group who is good with computers can be a big help.  A sample follows.

Use Stewardship Thoughts in Bulletin on Weekly basis

Use Stewardship Prayer of the Faithful on bi-monthly basis

Pastor to incorporate Stewardship in homilies as appropriate to readings (monthly).

MO.  	DAY      ACTIVITY               			PERSON RESPONSIBLE

Jan    	 6  	Evaluation of Renewal Weekend        		David/Trish

13  	Article in Parish Newsletter         			Judy

20  	Follow-up: confirm that volunteers contacted       	Phyllis/Becky

27  	Stewardship Committee Meeting 7:30         		Emily & Fr. B

Feb    	4 	Order Stewardship materials for bookrack   		Marcelle

6  	Commissioning Service for Volunteers          	Liturgy Committee

13	Question and Answer in Bulletin      		Bernadette

24	Stewardship Committee Meeting 7:30         		Emily & Fr. B

Mar    	6  	Welcome Breakfast for Newcomers      		Welcoming/Stewardship Committee

13 	Article in Parish Newsletter         			Judy

24	Stew Committee Meeting   7:30         		Emily & Fr. B

24	Plan Stewardship Appreciation Dinner       		Stewardship Committee

April  	7  	Mail invitations to Stew Dinner      			Susan

21  	Stew Committee Meeting 7:30          		Emily

29  	Stewardship Appreciation Dinner 7:00       		Stewardship Committee

May   	15  	Stewardship Question & Answer in Bulletin        	Bernadette

24  	Article in Newsletter                			Judy

25  	Evaluation of entire Stew. Program   		Carol

June 	5	Welcome Breakfast for Newcomers			Welcoming/Stewardship Committee

9-30 	Revise Time and Talent Booklet       		Susan/Greg/Trish

Take a Vacation!

July    	 12     	Plan Gift Discernment Workshop                     	KerryAnn/Joe/Fr. Bob

Get some Rest!

Aug 	14-15 	Begin planning Renewal Weekend       		Stewardship Committee

20  	Article in Newsletter				Judy

21 	Stew. literature in bookrack			Marcelle

26-28	Gift Discernment Workshop			Guest Presenters/Committee

Sept   	1  	Welcome Breakfast for Newcomers			Welcoming/Stewardship Committee

5	Stewardship Bulletin Board Up			Trisha/Becky

10-11   	Plan Ministry Fair				Greg/Trish

12-15 	Announce Children's essay contest			Phyllis

22  	Stew. Committee Meeting - 7:30			Emily/Fr. S

25  	Children's Stew in F. F. Classes			Carol

Oct    	  7  	Renewal materials to printer			Carol

18  	Art. in Newsltr.re:Renewal Weekend		Judy

17-18 	 Recruit Lay Witness Presenters			Bob /Phyllis

29  	Lay Witness Training session			Trisha/Becky

Nov  	1-4  	Prepare mailing for Renewal			Cassie

6  	Article in Bulletin				Fr. B

7-8  	Hang  Stewardship Banners			Bob

12-13 	Renewal Weekend - All Masses			Fr. & Committee

15  	Mailing of Brochure/Commitment Card		Mailing Committee

20  	Commitment Sunday				Fr. B

Dec    	 5  	Send TY cards					David/Susan

12  	TY in Bulletin					Bernadette